## Test Plan
🍔 SWIGGY — TEST PLAN
Project: Swiggy Food Delivery App ¦ QA Engineer: Soumyaranjan Sahoo
PROJECT NAME | Swiggy Food Delivery Application — Manual, Security & Cross-Platform / Mobile App Testing
QA ENGINEER | Soumyaranjan Sahoo
EMAIL | soumyaranjansahoo6530@gmail.com
GITHUB | github.com/soumyaranjansahoo5
TEST START DATE | 01-Jan-2025
TEST END DATE | 20-Jan-2025
APPLICATION TYPE | Web Application + Mobile Web (Android)
ENVIRONMENT | Staging / UAT
SCOPE OF TESTING | Functional, Regression, Smoke, Sanity, Security, Cross-Platform, Mobile App, API, SQL Backend Validation
OUT OF SCOPE | Performance Load Testing, iOS Testing, Payment Gateway Integration (Live)
MODULES IN SCOPE | 1. User Registration & Login 2. Restaurant Search & Filters 3. Menu & Item Selection 4. Cart Management 5. Coupon & Offer Application 6. Order Placement & Confirmation 7. Order Tracking (Real-time) 8. Payment (UPI / Wallet / COD) 9. Profile & Address Management 10. Push Notifications
TESTING TYPES | ✅ Functional ✅ Regression ✅ Smoke & Sanity ✅ Mobile App ✅ Cross-Platform ✅ Security ✅ BVA ✅ EP ✅ Negative ✅ White Box ✅ API (Postman) ✅ SQL Validation
ENTRY CRITERIA | 1. Build deployed on staging 2. Functional requirements signed off 3. Test cases reviewed and approved 4. Test data prepared 5. Postman collection ready
EXIT CRITERIA | 1. All P1/P2 bugs fixed and verified 2. Pass rate ≥ 80% 3. All critical modules smoke-tested 4. Test summary report signed off
TOOLS | JIRA ¦ Postman ¦ MySQL Workbench ¦ Chrome DevTools ¦ Android Real Device ¦ MS Excel ¦ Git & GitHub
BROWSERS | Chrome 124, Firefox 125, Microsoft Edge (Windows 11)
MOBILE DEVICES | Android 10, 11, 12 — Chrome Mobile (Real Device)
RISKS | 1. Unstable staging environment 2. Real device availability 3. Third-party payment gateway mocking 4. Dynamic data (restaurant availability, pricing)
ASSUMPTIONS | 1. Staging environment mirrors production 2. Test accounts and coupons provided 3. API docs available for Postman testing

## Test Cases
🍔 SWIGGY — TEST CASES
Manual Testing ¦ 95 Test Cases ¦ QA: Soumyaranjan Sahoo
TC ID | Module | Test Scenario | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority | Remarks
TC-001 | Login | Valid login with registered email | 1. Open Swiggy app 2. Enter valid email 3. Enter valid password 4. Click Login | Email: test@gmail.com Pwd: Test@123 | User logged in successfully, redirected to home | User logged in successfully | Pass | P1
TC-002 | Login | Login with invalid password | 1. Enter valid email 2. Enter wrong password 3. Click Login | Email: test@gmail.com Pwd: Wrong123 | Error: 'Invalid credentials' shown | Error message displayed | Pass | P1
TC-003 | Login | Login with unregistered email | 1. Enter unregistered email 2. Enter any password 3. Click Login | Email: notexist@test.com | Error: 'Account not found' shown | Error shown correctly | Pass | P1
TC-004 | Login | Login with empty email field | 1. Leave email blank 2. Enter password 3. Click Login | Email: (blank) | Validation: 'Email is required' | Validation triggered | Pass | P2
TC-005 | Login | Login with empty password field | 1. Enter valid email 2. Leave password blank 3. Click Login | Password: (blank) | Validation: 'Password is required' | Validation triggered | Pass | P2
TC-006 | Login | Login with SQL injection in email | 1. Enter SQL payload in email 2. Click Login | Email: ' OR '1'='1 | No login, input sanitized | Input sanitized, no bypass | Pass | P1 | Security
TC-007 | Login | OTP login flow | 1. Choose OTP login 2. Enter mobile number 3. Enter OTP | Mobile: 9668177321 | OTP received and login successful | OTP login worked | Pass | P1
TC-008 | Login | Session persistence after browser close | 1. Login 2. Close browser 3. Reopen app | Registered user | User remains logged in (remember me) | Session persisted | Pass | P2
TC-009 | Restaurant Search | Search by restaurant name | 1. Click search bar 2. Type restaurant name | Input: 'Dominos' | Dominos outlets listed | Results shown | Pass | P1
TC-010 | Restaurant Search | Search by cuisine type | 1. Click Cuisine filter 2. Select 'Biryani' | Filter: Biryani | All Biryani restaurants listed | Correct results | Pass | P2
TC-011 | Restaurant Search | Search with invalid name | 1. Type non-existent restaurant | Input: 'xyzabc123' | 'No restaurants found' message | Empty state shown | Pass | P2
TC-012 | Restaurant Search | Filter by rating ≥ 4.0 | 1. Apply rating filter ≥ 4.0 | Filter: 4.0+ | Only 4.0+ rated restaurants shown | Filter applied correctly | Pass | P2
TC-013 | Restaurant Search | Filter by delivery time < 30 min | 1. Apply delivery time filter | Filter: < 30 min | Restaurants within 30 min shown | Results filtered | Pass | P2
TC-014 | Restaurant Search | Filter by Veg Only | 1. Toggle Veg Only | Filter: Veg | Only veg restaurants listed | Veg filter works | Pass | P2
TC-015 | Cart | Add single item to cart | 1. Open restaurant 2. Click Add on item 3. Check cart | Item: Margherita Pizza | Item added, cart count = 1 | Item added correctly | Pass | P1
TC-016 | Cart | Add multiple items from same restaurant | 1. Add 3 different items | 3 items selected | All 3 in cart, total updated | Cart updated | Pass | P1
TC-017 | Cart | Add items from different restaurants | 1. Add item from Restaurant A 2. Try add from Restaurant B | Two restaurants | Warning: 'Clear cart?' prompt shown | Warning shown | Pass | P1
TC-018 | Cart | Remove item from cart | 1. Add item 2. Click minus/remove | 1 item in cart | Item removed, cart count = 0 | Item removed | Pass | P1
TC-019 | Cart | Increase item quantity to max limit | 1. Add item 2. Keep increasing qty | Qty: 1 to 20 | Max qty reached, + button disabled | Boundary handled | Pass | P2 | BVA
TC-020 | Cart | Cart persists after app refresh | 1. Add items 2. Refresh page | Items in cart | Cart items retained | Cart persisted | Pass | P2
TC-021 | Coupon | Apply valid coupon | 1. Go to cart 2. Enter coupon code 3. Apply | Code: SAVE50 | Discount applied, total reduced | Discount applied | Pass | P1
TC-022 | Coupon | Apply expired coupon | 1. Enter expired code | Code: OLDCODE10 | Error: 'Coupon expired' | Error shown | Pass | P1
TC-023 | Coupon | Apply invalid coupon code | 1. Enter random code | Code: XYZABC | Error: 'Invalid coupon' | Error shown | Pass | P1
TC-024 | Coupon | Apply coupon below minimum order | 1. Cart total < min order 2. Apply coupon | Total: ₹50, Min: ₹199 | Error: 'Min order ₹199 required' | Min order error shown | Pass | P2 | BVA
TC-025 | Coupon | Coupon manipulation via Postman | 1. Intercept request 2. Change coupon code to expired | Modified request | Server rejects tampered coupon | Server-side validation works | Pass | P1 | Security
TC-026 | Order | Place order with UPI payment | 1. Add items 2. Select UPI 3. Enter UPI ID 4. Confirm | UPI: test@upi | Order placed, confirmation shown | Order confirmed | Pass | P1
TC-027 | Order | Place order with wallet | 1. Add items 2. Select Swiggy Money 3. Confirm | Wallet balance: ₹500 | Order placed using wallet balance | Order placed | Pass | P1
TC-028 | Order | Place order with COD | 1. Add items 2. Select Cash on Delivery 3. Confirm | COD selected | Order placed with COD | COD order placed | Pass | P1
TC-029 | Order | Order with insufficient wallet balance | 1. Select wallet 2. Balance < order total | Wallet: ₹50, Order: ₹299 | Error: 'Insufficient balance' + top-up prompt | Error and prompt shown | Pass | P2
TC-030 | Order | Cancel order within cancellation window | 1. Place order 2. Cancel within 2 min | Order in 'Preparing' state | Order cancelled, refund initiated | Cancellation worked | Pass | P1
TC-031 | Order Tracking | Real-time tracking updates | 1. Place order 2. Open tracking screen | Active order | Driver location updates every 3-5 sec | Tracking updates | Pass | P1
TC-032 | Order Tracking | Tracking on poor network (2G) | 1. Switch to 2G 2. Open tracking | Network: 2G | Loader shown, graceful degradation | Graceful handling | Pass | P2 | Network
TC-033 | Order Tracking | ETA accuracy | 1. Place order 2. Check ETA vs actual | Order placed | ETA within ±5 min of actual | ETA accurate | Pass | P2
TC-034 | Payment | UPI payment with valid ID | 1. Enter valid UPI 2. Confirm payment | UPI: valid@upi | Payment success, receipt shown | Payment successful | Pass | P1
TC-035 | Payment | UPI payment with invalid ID | 1. Enter invalid UPI 2. Confirm | UPI: invalid_id | Error: 'Invalid UPI ID' | Error shown | Pass | P1
TC-036 | Payment | Boundary: order total = ₹0.01 | 1. Apply 100% coupon 2. Place order | Total: ₹0.01 | Order placed successfully | Min amount handled | Pass | P2 | BVA
TC-037 | Payment | Boundary: order total = ₹9999 | 1. Add items worth ₹9999 | Total: ₹9999 | Payment processed | Max amount handled | Pass | P2 | BVA
TC-038 | Mobile App | App loads on Android 12 | 1. Open Swiggy on Android 12 | Device: Samsung Galaxy | App loads within 3 sec | App loads correctly | Pass | P1 | Mobile
TC-039 | Mobile App | App loads on Android 11 | 1. Open Swiggy on Android 11 | Device: Redmi Note 10 | App loads, minor UI issue in cart | Cart badge misaligned | Fail | P2 | Bug: SWG-004
TC-040 | Mobile App | App loads on Android 10 | 1. Open Swiggy on Android 10 | Device: Realme C25 | App loads, notification delayed | Notification delay 8-12s | Fail | P3 | Bug: SWG-006
TC-041 | Mobile App | Touch target size — Add button | 1. Tap Add button on Android 11 | Device: Redmi | Button responds to touch | Touch target too small | Fail | P2 | Bug: SWG-005
TC-042 | Mobile App | Portrait/Landscape rotation | 1. Rotate device during browsing | Portrait → Landscape | App reorients, data preserved | Rotation handled | Pass | P3 | Mobile
TC-043 | Mobile App | Back button navigation | 1. Navigate deep 2. Press back | Deep navigation | Previous screen shown correctly | Back nav works | Pass | P2 | Mobile
TC-044 | Security | Direct URL access without login | 1. Copy order history URL 2. Logout 3. Paste URL in browser | Logged-out session | Redirected to login page | Auth bypass found | Fail | P1 | Bug: SWG-002 - CRITICAL
TC-045 | Security | Session token validity after logout | 1. Capture session token 2. Logout 3. Use captured token in Postman | Session token | Token rejected — 401 Unauthorized | Token not invalidated | Fail | P1 | Bug: SWG-001 - CRITICAL
TC-046 | Security | XSS in search field | 1. Enter XSS payload in search | Payload: <script>alert(1)</script> | Input sanitized, no alert | XSS blocked | Pass | P1 | Security
TC-047 | Security | SQL Injection in search | 1. Enter SQL payload | Payload: ' OR '1'='1 | Input sanitized | SQL injection blocked | Pass | P1 | Security
TC-048 | Cross-Platform | Chrome — full flow | 1. Complete end-to-end flow on Chrome | Browser: Chrome 124 | All features work | Pass | Pass | P1
TC-049 | Cross-Platform | Firefox — full flow | 1. Complete end-to-end flow on Firefox | Browser: Firefox 125 | All features work | Pass | Pass | P1
TC-050 | Cross-Platform | Edge — full flow | 1. Complete end-to-end flow on Edge | Browser: Edge | All features work | Pass | Pass | P1
TOTAL TEST CASES SHOWN (Full suite = 95)

## Bug Report
🍔 SWIGGY — BUG REPORT LOG
Total Bugs: 22 ¦ Critical: 2 ¦ High: 5 ¦ Medium: 9 ¦ Low: 6
Bug ID | Module | Bug Title | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Reported Date | Fixed Date
SWG-001 | Auth | Session token not invalidated after logout | 1. Login to Swiggy 2. Capture session token via DevTools 3. Logout from account 4. Use captured token in Postman GET /api/v1/profile | Token should return 401 Unauthorized | Token still returns 200 with user data | Critical | P1 | Fixed | 05-Jan-2025 | 12-Jan-2025
SWG-002 | Auth | Direct URL access to order history without login | 1. Login and copy Order History URL 2. Logout completely 3. Paste URL in new incognito tab | Should redirect to login page | Order history page loads without auth | Critical | P1 | Fixed | 05-Jan-2025 | 12-Jan-2025
SWG-003 | Coupon | Expired coupon accepted via Postman request | 1. Get expired coupon code 2. Intercept coupon apply request 3. Modify expiry param in Postman 4. Send request | Server should reject expired coupon | Coupon discount applied incorrectly | High | P2 | Fixed | 06-Jan-2025 | 14-Jan-2025
SWG-004 | Cart | Cart badge misaligned on Android < 360dp | 1. Open Swiggy on Redmi Note 10 (360dp) 2. Add item to cart 3. Check cart icon in header | Cart count badge should be top-right of icon | Badge overlaps icon boundary, partially hidden | High | P2 | Fixed | 08-Jan-2025 | 15-Jan-2025
SWG-005 | Mobile | Touch target too small on Apply Coupon (Android 11) | 1. Open cart on Android 11 2. Enter coupon code 3. Try tapping Apply button | Button should respond to first tap | Requires 2-3 taps, touch area < 44dp (Android guideline) | High | P2 | In Progress | 08-Jan-2025 | -
SWG-006 | Notification | Push notification delayed 8-12s on Android 10 | 1. Place order on Android 10 device 2. Note time of order confirmation 3. Check notification delivery time | Notification within 3 sec of event | Notification delayed 8-12 seconds on Android 10 | Medium | P3 | Open | 09-Jan-2025 | -
SWG-007 | Search | Empty state message missing when no restaurants found | 1. Search for 'xyzabc123' (non-existent) 2. Observe results area | 'No restaurants found' message shown | Blank white area, no feedback to user | Medium | P3 | Fixed | 07-Jan-2025 | 14-Jan-2025
SWG-008 | Payment | Wallet balance not refreshed after failed transaction | 1. Initiate payment via wallet 2. Simulate failure 3. Check wallet balance display | Balance should reflect actual amount | Balance shows pre-transaction amount (stale data) | Medium | P3 | Fixed | 10-Jan-2025 | 16-Jan-2025
SWG-009 | Order Tracking | Tracking map freezes after 5 min inactivity | 1. Place order 2. Open tracking screen 3. Leave screen idle 5+ min 4. Check map | Map should continue updating | Map freezes, requires pull-to-refresh | Low | P4 | Open | 11-Jan-2025 | -
SWG-010 | Profile | Address save fails silently on poor network | 1. Switch to 2G 2. Add new delivery address 3. Click Save | Error message or retry shown | No feedback shown, address not saved silently | Low | P4 | Open | 12-Jan-2025 | -
SWG-011 | Login | OTP resend timer not shown clearly | 1. Request OTP 2. Click Resend immediately | 30s cooldown timer visible | Resend button active but no timer countdown shown | Medium | P3 | Fixed | 06-Jan-2025 | 13-Jan-2025
SWG-012 | Cart | Cart total incorrect with multiple coupons | 1. Apply coupon 2. Add another item 3. Check total | Total recalculated correctly | Total shows pre-coupon price | High | P2 | Fixed | 09-Jan-2025 | 15-Jan-2025
SWG-013 | Search | Filter reset not working on back navigation | 1. Apply cuisine filter 2. Open restaurant 3. Press back | Filters should persist | Filters reset to default | Medium | P3 | Fixed | 07-Jan-2025 | 14-Jan-2025
SWG-014 | Mobile | Keyboard overlaps OTP input on Android 10 | 1. Open login on Android 10 2. Trigger OTP screen 3. Soft keyboard opens | OTP input visible above keyboard | OTP input hidden behind keyboard | Medium | P3 | Fixed | 08-Jan-2025 | 15-Jan-2025
SWG-015 | Payment | Surge price not shown before payment confirmation | 1. Order during peak hours 2. Proceed to payment | Surge pricing disclosed before confirm | Surge added silently in final total | High | P2 | Fixed | 10-Jan-2025 | 17-Jan-2025
SWG-016 | Order | Duplicate order on double-tap of Place Order | 1. Tap Place Order 2. Immediately tap again quickly | Only one order placed | Two orders created | Critical | P1 | Fixed | 11-Jan-2025 | 18-Jan-2025
SWG-017 | Notification | Order ready notification not sent for takeaway | 1. Place takeaway order 2. Wait for preparation | Notification when order ready | Notification never sent for takeaway type | Medium | P3 | Open | 12-Jan-2025 | -
SWG-018 | Search | Location permission denied — app crashes | 1. Deny location permission 2. Open search | Graceful error: 'Enable location' | App crashes (NullPointerException) | Critical | P1 | Fixed | 06-Jan-2025 | 12-Jan-2025
SWG-019 | Profile | Profile photo upload fails > 5MB | 1. Try uploading 6MB photo | Error: 'File too large' message | Silent failure, no error shown | Low | P4 | Fixed | 13-Jan-2025 | 18-Jan-2025
SWG-020 | Cart | Item quantity not validated — can set to 0 | 1. In cart set qty to 0 via keyboard | Item removed or validation shown | Item stays in cart with qty 0, breaks total | High | P2 | Fixed | 09-Jan-2025 | 16-Jan-2025
SWG-021 | Order Tracking | Estimated delivery time jumps unexpectedly | 1. Track active order 2. Observe ETA over 10 min | ETA decreases steadily | ETA jumps from 12 min to 25 min suddenly | Low | P4 | Open | 11-Jan-2025 | -
SWG-022 | Cross-Platform | Cart page layout broken on Firefox mobile emulation | 1. Open Firefox 2. Enable mobile emulation 3. Open cart | Layout consistent across browsers | Item cards overflow container on Firefox mobile | Medium | P3 | Fixed | 13-Jan-2025 | 19-Jan-2025

## Test Summary Report
🍔 SWIGGY — TEST SUMMARY REPORT
Final QA Report ¦ Soumyaranjan Sahoo ¦ Jan 2025
SECTION | DETAILS
Project Name | Swiggy Food Delivery Application
Test Cycle | Cycle 1 — Full Regression + Security
Test Period | 01-Jan-2025 to 20-Jan-2025
QA Engineer | Soumyaranjan Sahoo
Environment | Staging / UAT
Build Version | v3.24.1
EXECUTION SUMMARY
Total Test Cases | 95
Executed | 95
Passed | 73
Failed | 22
Blocked | 0
Skipped | 0
Pass Rate
BUG SUMMARY
Total Bugs Reported | 22
Critical Bugs | 4
High Bugs | 7
Medium Bugs | 7
Low Bugs | 4
Bugs Fixed & Verified | 16
Bugs Open | 6
MODULE-WISE PASS RATE
Login & Auth | 6/8 = 75%
Restaurant Search | 6/6 = 100%
Cart Management | 5/6 = 83%
Coupon | 4/5 = 80%
Order Placement | 4/5 = 80%
Order Tracking | 2/3 = 67%
Payment | 4/4 = 100%
Mobile App Testing | 3/6 = 50%
Security Testing | 2/4 = 50%
Cross-Platform | 3/3 = 100%
CONCLUSION | All Critical (P1) bugs have been fixed and verified. 2 High severity bugs remain open (in progress). Application is CONDITIONALLY APPROVED for release pending resolution of open P2 bugs in the next patch.
RECOMMENDATION | 1. Fix SWG-005 (touch target) before production 2. Monitor SWG-006 (Android 10 notifications) post-release 3. Re-test security module after auth fixes 4. Conduct regression on Cart and Payment modules after patch
QA SIGN-OFF | Soumyaranjan Sahoo — QA Engineer
DATE | 20-Jan-2025